## Sheet1
Final Project Management Schedule | Column1 | Column2 | Completed
Jobs | Team Member | Deadline
Finalize UML/EER | Noah | 2023-11-16 | yes
Write code to generate database tables | Jacob | 2023-11-24 | yes
Write program to query database from IDE | Noah | 2023-11-24 | in progress
Design UI layout | Ethan, Jacob | 2023-11-28 | in progress
Execute UI layout(WordPress or HTML?) | Ethan, Jacob | 2023-11-28 | yes
Design application backend | Jacob, Noah | 2023-11-28 | yes
Connect backend to web (REST API) | Ethan | 2023-12-02 | yes
Create final presentation | All | 2023-12-13 | in progress